**Mobile (iOS and Android) Application Milestone**

**Milestone: 1 (**It will take 5 working days and cost would be $700. Start date should be 14th Dec and End date 18th December**)**

• Registration, we will need to open the <http://setlr.com/> website in safari browser.

• Login: User will enter the email address and password for login in the application.

• For Recover Password: User will add the email and need to send the password to user account using API.

• Log-out: User will able to logout from the application.

• View Help: It would be static page with instructions (text & images).

• When application open then show the splash screen and remain for 2 or 3 second and redirect on home page or login page.

• In Home screen display the link related to Help, My Tasks, and create task.

• Create a Task: this is the main app feature, includes several stages. User will select the

Task from selected task “Answer A Question” and “Translate Something”

**Milestone: 2 (**It will take 9 working days and cost would be $1100. Start date should be 21st

Dec and End date 31st dec**)**

• If user selects the “Translate Something” then redirect on the “Translation Task” first step.

• In First Step,

o User will select the Source Language and Target Language from the dropdown list.

o User will select the relevance from the dropdown list. We need to get dropdown data from the API.

o User needs to fill 3 input fields (text only) like “What is it?”, “Context or Note to helper”, “Add Text to translate”.

o Or user will take a picture and we will need to send that picture to third party

OCR provider so we will get the text from the third party OCR provider ABBYY.

• In Second Step

o We need to calculate price based on the text and show to user (Calculation formula will be provided by you) in second step.

• In Third Step

o Once user will pay then we will need to pre- authorized this payment and payment should be completed once accept by the matching helper.

• If user selects the “Answer a Question” then redirect on the “Question Task” First Step

• In First Step,

o User will select and add the text as per <http://selt79.axshare.com/#p>=question\_task

o User will take a picture and we will need to send that picture to third party OCR

provider so we will get the text from the third party OCR provider ABBYY.

• In Second Step

o We need to calculate price based on the text and show to user (Calculation formula will be provided by you) in second step.

• In Third Step

o Once user will pay then we will need to pre- authorized this payment and payment should be completed once accept by the matching helper.

**Milestone: 3 (**It will take 7 working days and cost would be $900. Start date should be 1st Jan and End date 11th Jan**)**

• My Task

o User will see full history of created tasks. tasks are shown in order from the latest to the oldest, each task is shown with date, type, language pair, cost, View

button.

o User will able to view/manage the Task status e.g Open (submitted not taken, payment pre-authorized), Cancelled (removed from the list, payment remains pre authorized for set period then automatically voided. Only Open tasks can be cancelled), Pending (assigned to helper, payment taken, cannot be cancelled), Customer Review (Completed by Helper and returned to user.), Closed (Customer review task accepted by user. Payment made to Helper PayPal account. Best outcome.), In Revision (Customer review task marked for revision by user. Returned to original Helper for review. Second best outcome), Rejected (Customer review task marked rejected by user. Payment refunded to user.

Worst outcome.)

o User will able to view the details of any of the task and able to cancel the task which task status is only open.

o User will be able to Reopen and delete the Task as per define criteria in document.

**Milestone: 4 (**It will take 7 working days and cost would be $900. Start date should be 12th Jan and End date 22th Jan. We have holiday on 14th and 15th January due to Uttaryan festival**)**

• Helper Home Page: My Tasks, Up For Grabs, My History, Settings link.

• View Up For Grabs: User will see list of Open tasks here, matching stated language pairs. Each task will be shown with date & time, type, language pair, price\*, context

• View Task : User will see full task details here: user's name & photo, date & time, context, task text, attached files (if any), Grab Button

• Take Task: User clicks on Grab button - task changes status to Taken, this task is moved to user's list "My Tasks". Helper will able to take only 3 tasks simultaneously. Once this limit is reach helper's functionality for taking tasks is disabled.

**Milestone:5 (**It will take 5 working days and cost would be $600. Start date should be 22th Jan and End date 28th Jan**.** )

• Request Revision and Reject Task with push notification on customer side

• My Tasks, Process Task and Requested revision with push notification on helper side.

**Project Assumption**

• You will provide all design assets in required format and size.

• You will provide all API with documentation. If any API not working then you will provide the solution for it and might be delay in timeline due to that.

• For starting, We will use third party OCR provider ABBYY SDK and after that you will purchase that and provide us.

• If any other third party API or functionality need to purchase then you will purchase it and provide us.